## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2014-11-05
Group Number |  | 16
Participant 1 |  | Felix Hadinger
Participant 2 |  | Katarina Gmeiner
Participant 3 |  | Karim Salem
Participant 4 |  | Simon Marek
Participant 5 |  | Marcel Gössl
Mentor |  | Lilly Treml
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Research existing DICOM import Libraries | 15 | 14 | -1 | ja |  | Es sollen existierende Lösungen rund um DICOM Import gesucht werden
2 | Test existing DICOM Libraries | 20 | 30 | 10 | ja |  | Passende Codes rund um DICOM import sollen getestet werden, optimalerweise wird dadurch klar, mit welcher weitergearbeitet wird
3 | Get To Know Unity | 15 | 18 | 3 | ja |  | Alle Teammitglieder beschäftigen sich mit Unity, führen Installation durch
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  | 50 | 62 | 12 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol